## Sheet1
Date | Hour (B) | Subject | Description | Remarks | Dist (nm) | Time (u) | For | Status | Region | Weather | Navigation
2023-10-04 | 7:00 | Start mobilization |  |  |  |  | All | Finished | BEL Inshore | No impact | No impact
2023-10-04 | 8:00 | Daily meeting crew (TBC) | Briefing on planning of the day. |  |  |  | Crew | Finished | BEL Inshore | No impact | No impact
2023-10-04 | 9:00 | Provision delivery |  |  |  |  | Crew | Finished | BEL Inshore | No impact | No impact
2023-10-04 | 9:30 | Safety briefing | In scientific lab |  |  |  | Scientists | Finished | BEL Inshore | No impact | No impact
2023-10-04 | 10:00 | Operational meeting | Coordination first day. Procedures |  |  |  | Command team | Finished | BEL Inshore | No impact | No impact
2023-10-04 | 14:30 | ETD |  | When installation of pCO² system is completed. After heli exercise in dock sheduled between 1300 & 1500) |  |  | All | Finished | BEL Inshore | No impact | Possible impact
2023-10-04 | o/c | Transit | To Area 3A | @10kts | 80 | 8 | All | Finished | BEL EEZ | No impact | No impact
2023-10-04 | o/c | Abandon ship exercise |  |  |  |  | All | Finished | BEL TTW | No impact | No impact
2023-10-04 | o/c | FF exercise |  |  |  |  | All | Finished | BEL EEZ | No impact | No impact
2023-10-04 | 18:00 | Coordination meeting |  |  |  |  | Command team | Finished | Area 1 | No impact | No impact
2023-10-04 | 21:30 | Topas | ACW_03 @6kts SOG | E-W direction STW 0 before start iot lower drop keel -0,5m | 10 | 2 | All | Finished | Area 3a | No impact | No impact
2023-10-04 | 23:45 | Topas | ACW_02 @6kts SOG |  | 10 | 2 | All | Finished | Area 3a | No impact | No impact
2023-10-05 | 2:00 | Topas | ACW_01 @6kts SOG |  | 8 | 1.5 | All | Finished | Area 3a | No impact | No impact
2023-10-05 | 3:30 | Topas | ACW_07 @6kts SOG |  | 8 | 1.5 | All | Finished | Area 3a | No impact | No impact
2023-10-05 | hn | Topas | ACW_06 @6kts SOG |  | 12 | 2 | All | Finished | Area 3a | No impact | No impact
2023-10-05 | 7:00 | Topas | ACW_05 @6kts SOG - part I |  | 13 | 2.5 | All | Finished | Area 3a | No impact | No impact
2023-10-05 | 8:00 | Crew's meeting | @bridge |  |  |  | Crew | Finished | Area 3b | No impact | No impact
2023-10-05 | 9:30 | Vibrocoring | AC 07 | N-going current 09:38 VC in, heading 217, pos 52°22.011N 2°16.080E / 0952 VC out |  |  | All | Finished | Area 3a | No impact | No impact
2023-10-05 | 10:20 | Vibrocoring | AC 08 | N-going current 10:30 VC in, heading 240, pos 52°21.949N 2°16.133E / 1041 VC out |  |  |  | Finished |  | No impact | No impact
2023-10-05 | 11:20 | Vibrocoring | AC 09 | N-going current 11:32 VC in, heading 180, pos 52°21.855N 2°16.187E / 1145 VC out |  |  |  | Finished |  | No impact | No impact
2023-10-05 | 12:00 | Topas | ACW_05 @6kts SOG - part II |  |  |  | All | Finished | Area 3a | No impact | No impact
2023-10-05 | 14:00 | Vibrocoring | AC 12 | S-going current. 1405: VC in / 1415: VC out / heading: 002 pos: 52°20.613N 2°16.817E |  |  | All | Finished | Area 3a | Possible impact | No impact
2023-10-05 | 14:35 | Vibrocoring | AC 11 | S-going current. 1435: VC in, heading:354, pos: 52°21.073N 2°16.592E / 14:45: VC out Electric cable damaged. |  |  | All | Finished | Area 3a | Possible impact | No impact
2023-10-05 | 15:10 | CTD | Pos 52°21.132N 2°16.446E | Program change due to damaged cable 15:10 CTD in / 15:20 CTD out |  |  | All | Finished | Area 3a | Possible impact | No impact
2023-10-05 | 16:00 | Topas | ACW_04 @6kts SOG |  | 12 | 2 | All | Finished | Area 3a | No impact | No impact
2023-10-05 | TBC | Vibrocoring | AC 10 | S-going current. Cancelled due to cable rupture (repair needs 24hr to dry) |  |  | All | Cancelled | Area 3a | Possible impact | No impact
2023-10-05 | TBC | Vibrocoring | AC4 & 1 (TBC) | AC_02: 0,1NM from cable AC_02: < 0,4NM from cable |  |  |  | Cancelled |  | Possible impact
2023-10-05 | 18:00 | Coordination meeting | @bridge |  |  |  | Command team | Finished | Area 3a | No impact | No impact
2023-10-05 | 18:20 | Transit | To Area 3b @ 6kts. | Topas on | 16 | 2 |  | Finished |  | No impact | No impact
2023-10-05 | 21:30 | CTD | [5 empty] | Finished | Area 3b | No impact | No impact
2023-10-05 | 22:00 | Topas | ACE_07 @5kts SOG |  | 13.5 | 2.5 | All | Finished | Area 3b | Possible impact | No impact
2023-10-06 | 0:30 | Topas | ACE_06 @5kts SOG |  | 15.5 | 3 | All | Finished | Area 3b | Possible impact | No impact
2023-10-06 | 3:30 | Topas | ACE_05 @5kts SOG |  | 16.5 | 4 | All | Finished | Area 3b | Possible impact | No impact
2023-10-06 | 7:30 | Topas | ACE_04 @5kts SOG | Start ivo WMF | 16 | 3 | All | Finished | Area 3b | Possible impact | Possible impact
2023-10-06 | 8:00 | Crew's meeting | @bridge |  |  |  | Crew | Finished | Area 3b | No impact | No impact
2023-10-06 | 10:00 | Topas | ACE_03 @5kts SOG |  | 12.5 | 2.5 | All | Finished | Area 3b | Possible impact | Possible impact
2023-10-06 | 12:30 | Topas | ACE_02 @5kts SOG |  | 13 | 3 | All | Finished | Area 3b | Possible impact | Possible impact
2023-10-06 | 15:30 | Topas | ACE_01 (E-W) @5kts SOG |  | 8 | 2 | All | Finished | Area 3b | Possible impact | Possible impact
2023-10-06 | 15:45 | CTD | End of ACE_01 |  |  |  | All | Finished | Area 2 | Possible impact | Possible impact
2023-10-06 | 16:00 | Topas | NL_05 (W-E) @5kts SOG | North Hinder North TSS & Maas West Outer TSS | 20 | 4 | All | Finished | Area 2 | Possible impact | Possible impact
2023-10-06 | 18:00 | Coordination meeting | @bridge |  |  |  | Command team | Finished | Area 2 | Possible impact | No impact
2023-10-06 | 20:15 | Topas | NL_10 @5kts SOG | North Hinder North TSS & Maas West Outer TSS | 20 | 4 | All | Finished | Area 2 | Possible impact | Possible impact
2023-10-06 | 21:00 | Rugby | @dayroom. FR vs IT | Heading not between 260-280 |  |  | All | Finished |  | Possible impact | No impact
2023-10-07 | 0:00 | Topas | NL_11 @5kts SOG | North Hinder North TSS & Maas West Outer TSS | 20 | 4 | All | Finished | Area 2 | Possible impact | Possible impact
2023-10-07 | 4:00 | Topas | NL_12 @5kts SOG | North Hinder North TSS | 17 | 3.5 | All | Finished | Area 2 | Possible impact | Possible impact
2023-10-07 | 7:20 | Topas | NL_13 @5kts SOG | North Hinder North TSS | 20 | 4 | All | Finished | Area 2 | Possible impact | Possible impact
2023-10-07 | 8:00 | Crew's meeting |  |  |  |  | Crew | Finished | Area 2 | Possible impact | No impact
2023-10-07 | 10:17 | CTD | pos 52°9.437N 3°17.064E | 10:30 CTD on board |  |  | All | Finished | Area 2 | Possible impact | Possible impact
2023-10-07 | 13:00 | Topas | NL_14 @5kts SOG | TSS crossing | 26 | 5.5 | All | Finished | Area 2 | Possible impact | Possible impact
2023-10-07 | 14:00 | Fire drill |  |  |  |  | Crew | Finished |  | No impact | No impact
2023-10-07 | 15:45 | Transit | To area 5, at max speed for Topas Follow OSP1 (ETA 00:30), TSS, OSP 4 (ETA 06:00), OSP 5 (ETA 0800) |  | 81 | 9 |  | Finished | Area 4 | No impact | No impact
2023-10-07 | 18:00 | Coordination meeting |  |  |  |  | Command team | Finished | Area 1 | No impact | No impact
2023-10-07 | 20:30 | briefing project |  | All welcome - science meeting room level 6 |  |  | All | Finished | Area 4 | No impact | No impact
2023-10-07 | 21:00 | CTD | Along navtrack | 52°44,2N 002°46,2E |  |  |  | Finished | Area 4 | No impact | No impact
2023-10-08 | 0:30 | Topas | OSP1 | Along transit, at max speed for Topas on 1 big gen |  |  |  | Finished | Area 4 | No impact | No impact
2023-10-08 | o/c | Transit |  | at max speed for Topas on 1 big gen |  |  |  | Finished | Area 4 | No impact | No impact
2023-10-08 | 6:40 | Topas | OSP4 | at max speed for Topas on 1 big gen |  |  |  | Finished | Area 4 | No impact | No impact
2023-10-08 | 8:00 | Crew's meeting |  |  |  |  | Crew | Finished | Area 4 | No impact | No impact
2023-10-08 | 8:30 | Topas | OSP5 | at 5 kts | 20 | 4 |  | Finished | Area 4 | No impact | No impact
2023-10-08 | 12:30 | Topas | DB13 | @5kts | 23 | 5 |  | Finished | Area 5 | No impact | No impact
2023-10-08 | 14:00 | Safety committee | [5 empty] | Finished | Area 5 | No impact | No impact
2023-10-08 | 17:30 | Topas | DB14 | @5kts | 25 | 5 |  | Finished | Area 5 | No impact | No impact
2023-10-08 | 18:00 | Coordination meeting |  |  |  |  | Command team | Finished | Area 5 | No impact | No impact
2023-10-08 | 21:00 | CTD |  | 54°38,0N 003°17,6E |  |  |  | Finished | Area 5 | No impact | No impact
2023-10-08 | 22:30 | Topas | DB15 | @5kts | 11 | 2 |  | Finished | Area 5 | No impact | No impact
2023-10-08 | 0:30 | Topas | DB16 | @5kts | 22 | 5 |  | Finished | Area 5 | No impact | No impact
2023-10-09 | 6:10 | Topas | DB17, pt 1 | @5kts | 19 | 4 |  | Finished | Area 5 | No impact | No impact
2023-10-09 | 8:00 | Crew's meeting |  |  |  |  | Crew | Finished | Area 5 | No impact | No impact
2023-10-09 | 9:00 | CTD |  | position: 54°41.3187N 2°56.9209E |  |  |  | Finished | Area 5 | No impact | No impact
2023-10-09 | 10:00 | Vibrocoring | VC03 | 1010 VC In, heading 300, pos 54°39.325N 003°0.373E / 1017 VC Out |  |  |  | Finished | Area 5 | No impact | No impact
2023-10-09 | 10:45 | Vibrocoring | VC04 | heading 305, pos 54°39.533N 3°0.616E / 1052 VC in / 1059 VC out |  |  |  | Finished | Area 5 | No impact | No impact
2023-10-09 | 10:22 | Vibrocoring | 0 | heading 305, pos 54°39.166N 3°0.191E / 1124 VC in / 1131 VC out |  |  |  | Finished | Area 5 | No impact | No impact
2023-10-09 | 11:50 | Vibrocoring | VC01 | heading 305, pos 54°38.746N 2°59.711E / 1158 VC in / 1206 VC out |  |  |  | Finished | Area 5 | No impact | No impact
2023-10-09 | 12:30 | Topas | DB 17, pt 2 | @5kts | 27 | 6 |  | Finished | Area 5 | No impact | No impact
2023-10-09 | 13:30 | Topas | DB18, pt 1 | @5kts |  |  |  | Finished | Area 5 | No impact | No impact
2023-10-09 | 15:00 | Vibrocoring | VC05 | heading 325 , pos 54°40.467N 2°1.685E / 1502 VC in / 1508 VC out |  |  |  | Finished | Area 5 | No impact | No impact
2023-10-09 | 15:30 | Transit | To Vibrocore position |  |  |  |  | Finished | Area 5 | No impact | No impact
2023-10-09 | 17:00 | Vibrocoring | VC10 | Pos: 54°47.968N-003°20.715E heading 302 / 1649 VC in / 1658 VC out |  |  |  | Finished | Area 5 | No impact | No impact
2023-10-09 | 17:15 | Vibrocoring | VC09 | Pos: 54°48.083N-003°20.358E heading 302 / 1716 VC in / 1725 VC out |  |  |  | Finished | Area 5 | No impact | No impact
2023-10-09 | 18:00 | Vibrocoring | VC08 | Pos: 54°48.292N-003°19.737E heading 300 / 1746 VC in / 1754 VC out |  |  |  | Finished | Area 5 | No impact | No impact
2023-10-09 | 18:30 | Vibrocoring | VC06 | Pos: 54°48.637N-003°18.702E heading 305 / 1820 VC in / 1829 VC out / 3m ahead pos: 54°48.638N-003°18.700E / 1843 VC in / 1853 VC out |  |  |  | Finished | Area 5 | No impact | No impact
2023-10-09 | 19:30 | Vibrocoring | VC07 | Pos: 54°49.670N-003°20.114E heading 305 / 1922 VC in / 1931 VC OUT |  |  |  | Finished | Area 5 | No impact | No impact
2023-10-09 |  | CTD |  | CTD in same position as last core |  |  |  | Finished
2023-10-09 | 19:30 | Transit | to DB 18, pt 2 | 6,5kts |  |  |  | Finished | Area 5 | No impact | No impact
2023-10-09 | TBD | Coordination meeting |  |  |  |  | Command team | Finished | Area 5 | No impact | No impact
2023-10-09 | 22:00 | Topas | DB18, pt 2 | 6,5kts | 20 | 3.5 |  | Finished | Area 5 | No impact | No impact
2023-10-10 | 1:30 | Topas | DB19 | 6,5kts | 11 | 2 |  | Finished | Area 5 | No impact | No impact
2023-10-10 | 3:30 | Topas | DB20 | 6,5kts | 17 | 3 |  | Finished | Area 5 | No impact | No impact
2023-10-10 | 5:45 | transit | To Vibrocore position | max speed | 23 | 3 |  | Finished | Area 6 | No impact | No impact
2023-10-10 | 8:00 | Crew's meeting |  |  |  |  | Crew | Finished | Area 6 | No impact | No impact
2023-10-10 | 8:44 | Vibrocoring (TBC) | OG05 | In position 54°22.347N 4°7.880E, heading 221 / 0846 VC In / 0856 VC out |  |  |  | Finished | Area 6 | No impact | No impact
2023-10-10 | 9:26 | Vibrocoring | OG04 | In position 54°22.222N 4°5.435E, heading 235 / 0928VC In / 0937 VC out |  |  |  | Finished | Area 6 | No impact | No impact
2023-10-10 | 9:40 | transit | to OG3 |  |  |  |  | Finished | Area 6 | No impact | No impact
2023-10-10 | 10:30 | Vibrocoring | OG3 | In position 54°21.696N 3°55.127E, heading 255 / 1034 VC In / 1042 VC out |  |  |  | Finished | Area 6 | No impact | No impact
2023-10-10 | 10:45 | transit | to OG2 |  |  |  |  | Finished | Area 6 | No impact | No impact
2023-10-10 | 11:30 | Vibrocoring | OG2 | In position 54°21.197N 3°45.308E, heading 220 / 1138 VC In / 1145 VC out / 5m ahead / 1155 VC In / 1207 VC out |  |  |  | Finished | Area 6 | No impact | No impact
2023-10-10 | 12:10 | Transit | to OG1 |  |  |  |  | Finished | Area 6 | No impact | No impact
2023-10-10 | 12:30 | Vibrocoring | OG1 | In position 54°20.929N 3°40.049E, heading 214 / 1248 VC In / 1256 VC out |  |  |  | Finished | Area 6 | No impact | No impact
2023-10-10 | 13:00 | CTD | [5 empty] | Finished | Area 6 | No impact | No impact
2023-10-10 | 14:00 | transit | to OG01 W side | max speed on 1 DG | 10 | 1 |  | Finished | Area 6 | No impact | No impact
2023-10-10 | 15:00 | Topas | OG01 | 9kts | 33 | 4 |  | Finished | Area 6 | No impact | No impact
2023-10-10 | 18:00 | Coordination meeting |  |  |  |  | Command team | Finished | Area 6 | No impact | No impact
2023-10-10 | 18:30 | Transit |  | max speed on 1 DG | 10 | 1 |  | Finished
2023-10-10 | 19:30 | Topas | OG03 | 6,5 kts | 8.5 | 1.5 |  | Finished | Area 6 | No impact | No impact
2023-10-10 | 20:00 | Silke's talk | Silke will give a talk about her research; level 6; science meeting room; all welcome |  |  |  | Everyone is welcone | Finished | Area 6 | No impact | No impact
2023-10-10 | 21:00 | Transit |  | max speed on 1 DG | 1.3 | 0.5 |  | Finished
2023-10-10 | 21:30 | Topas | OG04 | 6,5 kts | 8.5 | 1.5 |  | Finished | Area 6 | No impact | No impact
2023-10-10 | 23:00 | Transit |  | max speed on 1 DG | 6 | 1 |  | Finished
2023-10-11 | 0:00 | Topas | OG05 | 6,5 kts | 8.5 | 1.5 |  | Finished | Area 6 | No impact | No impact
2023-10-11 | 1:30 | Transit |  | max speed on 1 DG | 6 | 0.5 |  | Finished
2023-10-11 | 2:00 | Topas | OG06 | 6,5 kts - if need be, skip this one Partially finished, in order to be in time in CTD station | 8.5 | 1.5 |  | Finished | Area 6 | No impact | No impact
2023-10-11 | 3:30 | transit from OG06 to CTD |  | max speed on 1 DG | 37 | 4 |  | Finished
2023-10-11 | 6:00 | CTD | OSP01 | 54°07.0512N 2°41.0453E |  |  |  | Finished | Area 4 | No impact
2023-10-11 | 6:30 | transit to CTD |  |  | 14 | 1.5 |  | Finished | Area 4 | No impact
2023-10-11 | 8:00 | Crew's meeting |  |  |  |  | Crew | Finished | Area 4 | No impact | No impact
2023-10-11 | 8:25 | CTD | OSP04 | 53°57.4307N 2°56.9838E |  |  |  | Finished | Area 4 | No impact
2023-10-11 | 8:50 | Transit |  | 4 | 105 | 13 |  | Finished | Area 4 | No impact
2023-10-11 | 18:00 | Coordination meeting |  |  |  |  | Command team | Finished | Area 1 | No impact | No impact
2023-10-11 | 21:30 | Sparker deployement | current: 1,2kts, dir: 203 2,5NM before start of SB_08, reduce speed to min manoeuvring speed and preapre aft deck. Deplo gear when ready |  |  |  |  | Finished | Area 1 | No impact
2023-10-11 | 22:30 | Sparker & Topas | SB_08 (W-E) @3,5kts SOG |  | 24 | 6.8571 | All | Finished | Area 1 | No impact | No impact
2023-10-12 | 6:30 | Sparker & Topas | SB_07 @3,5kts STW |  | 22 | 6.2857 | All | Finished | Area 1 | No impact | No impact
2023-10-12 | 8:00 | Crew's meeting |  |  |  |  | Crew | Finished | Area 1 | No impact | No impact
2023-10-12 | 10:00 | Sparker & Topas | SB_06 @3,5kts STW |  | 19 | 5.4286 | All | Finished | Area 1 | No impact | No impact
2023-10-12 | 14:30 | Bomb threat briefing |  | Conference room |  |  | Crew | Finished | Area 1 | No impact | No impact
2023-10-12 | 16:00 | SSAS test |  |  |  |  | Crew | Finished | Area 1 | No impact | No impact
2023-10-12 | 16:00 | Sparker & Topas | SB_05 @3,5kts STW |  | 23 | 6.5714 | All | Finished | Area 1 | No impact | No impact
2023-10-12 | 18:00 | Coordination meeting |  |  |  |  | Command team | Finished | Area 1 | No impact | No impact
2023-10-13 | 23:00 | Sparker & Topas | SB_04 @3,5kts STW |  | 27 | 7.7143 | All | Finished | Area 1 | Possible impact | No impact
2023-10-13 | 4:30 | Sparker recovery | When weather has deteriorated and image is to bad. Wake up CO and Sparker technician first in order to evaluate. After decision, wake up boatswain & 2nd boatswain 15' in advance. | Expected around 0500 |  |  |  | Finished | Area 1 | Possible impact
2023-10-13 | 5:30 | Topas | SB_03 @6kts SOG | Until image deteriorates | 24 | 6.8571 | All | Finished | Area 1 | Possible impact | No impact
2023-10-13 | 8:00 | Crew's meeting |  |  |  |  | Crew | Finished | Area 1 | No impact | No impact
2023-10-13 | 9:00 | Topas | SB_02 @6kts SOG | North Hinder South & Sunk TSS | 23 | 6.5714 | All | Finished | Area 1 | Possible impact | Possible impact
2023-10-13 | 13:15 | Transit/Topas | SB_01 (E-W) @6kts SOG | Bad quality due to weather. Intend to sail at higher speed to other side and start with currents in the back . | 27 | 7.7143 | All | Finished | Area 1 | Possible impact | Possible impact
2023-10-13 | TBD | Sheltering | N of WMF / UK anchor area |  |  |  |  | Cancelled | Area 1 | Possible impact
2023-10-13 | 16:05 | Topas | SB_01 (E-W) @6kts SOG |  | 27 |  |  | Finished | Area 1 | Possible impact | Possible impact
2023-10-13 | 16:10 | Slow flooding incident | In hospital. Rupture of hot water pipe, causing smoke detection system to go off. No impact on mission. Impact on hospital TBC. |  |  |  |  | Finished | Area 1 | No impact | No impact
2023-10-13 | 18:00 | Coordination meeting |  |  |  |  | Command team | Finished | Area 1 | No impact | No impact
2023-10-13 | 20:30 | CTD | Start of line SB_11 |  |  |  |  | Finished | Area 1
2023-10-13 | 21:00 | Topas | SB_11 @6kts SOG | 2 | 27 | 7.7143 | All | Finished | Area 1 | Possible impact | Possible impact
2023-10-14 | 1:30 | CTD | [5 empty] | Finished | Area 1 | Possible impact | No impact
2023-10-14 | 2:00 | Topas | SB_10 @6kts SOG | With direction TSS | 27 | 7.7143 | All | Finished | Area 1 | Possible impact | Possible impact
2023-10-14 | 6:00 | Transit/Topas | To test zone |  |  |  |  | Finished | Area 1
2023-10-14 | 8:00 | Crew's meeting | [5 empty] | Finished | Area 1 | No impact | No impact
2023-10-14 | 8:00 | DP tests | [5 empty] | Finished | Area 1 | Possible impact | No impact
2023-10-14 | 10:00 | ADCP test | [5 empty] | Finished | Area 1 | Possible impact | No impact
2023-10-14 | 13:00 | Transit | [5 empty] | Ongoing | Area 1 | No impact | No impact
2023-10-14 | 14:00 | briefing project | For crew |  |  |  |  | Ongoing | Area 1 | No impact | No impact
2023-10-07 | 14:00 | Vibrocoring | DCS_VC01 | Direction( S-N)dependant on current ==> point order might change |  |  | All | Cancelled | Area 2 | Possible impact | No impact
2023-10-07 | 15:00 | Vibrocoring | DCS_VC02 | Direction( S-N)dependant on current ==> point order might change |  |  | All | Cancelled | Area 2 | Possible impact | No impact
2023-10-07 | 16:00 | Vibrocoring | DCS_VC03 | Direction( S-N)dependant on current ==> point order might change |  |  | All | Cancelled | Area 2 | Possible impact | No impact
2023-10-07 | 17:00 | Vibrocoring | DCS_VC04 | Direction( S-N)dependant on current ==> point order might change |  |  | All | Cancelled | Area 2 | Possible impact | No impact
2023-10-07 | 18:00 | CTD | CTD_NL_02 |  |  |  | All | Cancelled | Area 2 | No impact | No impact
2023-10-10 | 9:00 | Vibrocoring |  | Time/Place issue. Should start transit at 06:00 iot arrive at 09:00. Prio? From this moment, end of torough analysis of operational course. 8 cores are mentioned in plan, however only 6 positions available. In deep water route. AX_VC17: 0,47NM from cable AX_VC20: 0,1NM from pipe |  |  | All | Cancelled | Area 3b |  | Possible impact
2023-10-14 | 17:30 | ETA | Breakwaters Zeebrugge |  |  |  | All | Planned | BEL Inshore | No impact | No impact
2023-10-14 | 18:32 | ETA | Naval port Zeebrugge |  |  |  | All | Planned | BEL Inshore | No impact | No impact
2023-10-14 | O/C mooring | Payment meal + goodies | In conference room | Put in order for goodies NLT 1800 in conference room
2023-10-14 | 20:00 | science debrief | Scientists gather in conference room for final debrief |  |  |  | Scientists
2023-10-15 | 8:00 | Crew's meeting |  | In scientist lab
2023-10-15 | o/c | Coordination meeting | CO, chief engineer, chief mate, electronician, boatswain, Lt Nav | In scientist lab Overview of 16 - 20 okt
2023-10-15 | 8:00 | Demob |  | Vibrocorrer will stay ashore until Tuesday |  |  | All | Planned | BEL Inshore | No impact | No impact

## Feuil1
dist | speed | hrs | days | hrs
568 | 8 | 71 | 2.9583 | -1
| 9 | 63.1111
| 10 | 56.8 | 2.3667 | 8.8
568 | 8.7385 | 65
12 |  | 2

## List
Position Type | Region | Status | For | Weather | Navigation
Approx. | Area 1 | Planned | Scientists | No impact | No impact
Exact | Area 2 | Ongoing | Crew | Possible impact | Possible impact
| Area 3a | Finished | All | Interruption | Heavy impact
| Area 3b | Cancelled | Command team
Area 4
Area 5
Area 6
Area 7
BEL EEZ
BEL Inshore
BEL TTW
NDL EEZ
NDL TTW
UK EEZ
UK TTW

## sheet1 EARS
[5 empty] | In many cases tools can be omitted. Ie "Station" or "Line" only makes sense for the Belgica as a whole. | Effectively, when the row say "Topas ACE_03 @5kts SOG" this does not mean "Topas bottom profiler activated". It means, "Belgica started with line ACE_03 of Topas" | If all actions are "Start" we can simplify this and omit this column. However, please note some "End" at the end. In the final template, we can leave "Start" as the default, and can be modified if need be. |  | Sometimes this still has remarksy stuff, such as @6kts SOG | Description and remarks are indeed 2 separate things. I have combined many of them but this feels dirty. Description is an elaboration of the label, or a description of the results of the action. Remarks are rather "sideways remarks of importance in another context". EARS has no remarks field. Should we add one? | [10 empty] | Distance_nm is only given when the Process is a line or a transit. We can do this easily in EARS properties. | As all events are understood to be Starts, this is the duration of the action. |  | Please note "Canceled" column. We may include something like this in EARS. | This may be added as a property, as a less specific area description than the station
| Note wonky times, probably meant as "symbolic time". Note "TBC": this is an EXECUTED program, right? |  |  |  | The For column has been subsumed here under Crew, All, Scientists. I still need to find a good synonym for all as in "All persons aboard, passengers/scientists+crew+command", and not "All tools". Because these will need to be defined as "Tools" all hands | It is clear, for each type of cruise BMDC needs to look at these logs to make sense of them and harmonize them |  |  |  | In general I didn't copy pure coordinates as EARS can calculate those
Some transits have no label. In general our label corresponds to the original description
| B |  | UUIDs | [8 empty] | properties | properties | properties | properties | properties | properties
Date | Hour | Actor | eventDefinitionId | Program | Tool | Process | Action | Label | Station | Description | Remarks | Dist | Time | Status | Region | Weather | Navigation | Subject | Description2 | Remarks2 | Dist (nm)2 | Time (u)3 | For4 | Status5 | Region6 | Weather7 | Navigation8 | original order
|  |  |  | 11BU_operations | Topas | Operation | Start
2023-10-04 | 7:00 |  |  | 11BU_operations | Belgica | Mobilisation | Start | [10 empty] | Start mobilization |  |  |  |  | All | Finished | BEL Inshore | No impact | No impact | 1
2023-10-04 | 8:00 |  |  | 11BU_operations | Crew | Meeting | Start | Daily meeting crew (TBC) | [9 empty] | Daily meeting crew (TBC) | Briefing on planning of the day. |  |  |  | Crew | Finished | BEL Inshore | No impact | No impact | 2
2023-10-04 | 9:00 |  |  | 11BU_operations | Crew | ???? | Start | [10 empty] | Provision delivery |  |  |  |  | Crew | Finished | BEL Inshore | No impact | No impact | 3
2023-10-04 | 9:30 |  |  | 11BU_operations | Scientists | Meeting | Start | Safety briefing | [9 empty] | Safety briefing | In scientific lab |  |  |  | Scientists | Finished | BEL Inshore | No impact | No impact | 4
2023-10-04 | 10:00 |  |  | 11BU_operations | Command | Meeting | Start | Operational meeting | [9 empty] | Operational meeting | Coordination first day. Procedures |  |  |  | Command team | Finished | BEL Inshore | No impact | No impact | 5
2023-10-04 | 14:30 |  |  | 11BU_operations | Belgica | Cruise | Start |  |  | When installation of pCO² system is completed. After heli exercise in dock sheduled between 1300 & 1500) | [7 empty] | ETD |  | When installation of pCO² system is completed. After heli exercise in dock sheduled between 1300 & 1500) |  |  | All | Finished | BEL Inshore | No impact | Possible impact | 6
2023-10-04 | o/c |  |  | 11BU_operations | Belgica | Transit | Start | To Area 3A |  | @10kts | [7 empty] | Transit | To Area 3A | @10kts | 80 | 8 | All | Finished | BEL EEZ | No impact | No impact | 7
2023-10-04 | o/c |  |  | 11BU_operations | All | Exercise | Start | Abandon ship exercise | [9 empty] | Abandon ship exercise |  |  |  |  | All | Finished | BEL TTW | No impact | No impact | 8
2023-10-04 | o/c |  |  | 11BU_operations | All | Exercise | Start | FF exercise | [9 empty] | FF exercise |  |  |  |  | All | Finished | BEL EEZ | No impact | No impact | 9
2023-10-04 | 18:00 |  |  | 11BU_operations | Command | Meeting | Start | Coordination meeting | [9 empty] | Coordination meeting |  |  |  |  | Command team | Finished | Area 1 | No impact | No impact | 10
2023-10-04 | 21:30 |  |  | 11BU_operations | Belgica | Line | Start | Topas | ACW_03 @6kts SOG | E-W direction STW 0 before start iot lower drop keel -0,5m | [7 empty] | Topas | ACW_03 @6kts SOG | E-W direction STW 0 before start iot lower drop keel -0,5m | 10 | 2 | All | Finished | Area 3a | No impact | No impact | 11
2023-10-04 | 23:45 |  |  | 11BU_operations | Belgica | Line | Start | Topas | ACW_02 @6kts SOG | [8 empty] | Topas | ACW_02 @6kts SOG |  | 10 | 2 | All | Finished | Area 3a | No impact | No impact | 12
2023-10-05 | 2:00 |  |  | 11BU_operations | Belgica | Line | Start | Topas | ACW_01 @6kts SOG | [8 empty] | Topas | ACW_01 @6kts SOG |  | 8 | 1.5 | All | Finished | Area 3a | No impact | No impact | 13
2023-10-05 | 3:30 |  |  | 11BU_operations | Belgica | Line | Start | Topas | ACW_07 @6kts SOG | [8 empty] | Topas | ACW_07 @6kts SOG |  | 8 | 1.5 | All | Finished | Area 3a | No impact | No impact | 14
2023-10-05 | hn |  |  | 11BU_operations | Belgica | Line | Start | Topas | ACW_06 @6kts SOG | [8 empty] | Topas | ACW_06 @6kts SOG |  | 12 | 2 | All | Finished | Area 3a | No impact | No impact | 15
2023-10-05 | 7:00 |  |  | 11BU_operations | Belgica | Line | Start | Topas | ACW_05 @6kts SOG - part I | [8 empty] | Topas | ACW_05 @6kts SOG - part I |  | 13 | 2.5 | All | Finished | Area 3a | No impact | No impact | 16
2023-10-05 | 8:00 |  |  | 11BU_operations | Crew | Meeting | Start | Crew's meeting |  | @bridge | [7 empty] | Crew's meeting | @bridge |  |  |  | Crew | Finished | Area 3b | No impact | No impact | 17
2023-10-05 | 9:30 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | AC 07 | N-going current 09:38 VC in, heading 217, pos 52°22.011N 2°16.080E / 0952 VC out | [7 empty] | Vibrocoring | AC 07 | N-going current 09:38 VC in, heading 217, pos 52°22.011N 2°16.080E / 0952 VC out |  |  | All | Finished | Area 3a | No impact | No impact | 18
2023-10-05 | 10:20 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | AC 08 | N-going current 10:30 VC in, heading 240, pos 52°21.949N 2°16.133E / 1041 VC out | [7 empty] | Vibrocoring | AC 08 | N-going current 10:30 VC in, heading 240, pos 52°21.949N 2°16.133E / 1041 VC out |  |  |  | Finished |  | No impact | No impact | 19
2023-10-05 | 11:20 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | AC 09 | N-going current 11:32 VC in, heading 180, pos 52°21.855N 2°16.187E / 1145 VC out | [7 empty] | Vibrocoring | AC 09 | N-going current 11:32 VC in, heading 180, pos 52°21.855N 2°16.187E / 1145 VC out |  |  |  | Finished |  | No impact | No impact | 20
2023-10-05 | 12:00 |  |  | 11BU_operations | Belgica | Line | Start | Topas | ACW_05 @6kts SOG - part II | [8 empty] | Topas | ACW_05 @6kts SOG - part II |  |  |  | All | Finished | Area 3a | No impact | No impact | 21
2023-10-05 | 14:00 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | AC 12 | S-going current. 1405: VC in / 1415: VC out / heading: 002 pos: 52°20.613N 2°16.817E | [7 empty] | Vibrocoring | AC 12 | S-going current. 1405: VC in / 1415: VC out / heading: 002 pos: 52°20.613N 2°16.817E |  |  | All | Finished | Area 3a | Possible impact | No impact | 22
2023-10-05 | 14:35 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | AC 11 | S-going current. 1435: VC in, heading:354, pos: 52°21.073N 2°16.592E / 14:45: VC out Electric cable damaged. | [7 empty] | Vibrocoring | AC 11 | S-going current. 1435: VC in, heading:354, pos: 52°21.073N 2°16.592E / 14:45: VC out Electric cable damaged. |  |  | All | Finished | Area 3a | Possible impact | No impact | 23
2023-10-05 | 15:10 |  |  | 11BU_operations | Belgica | Station | Start | CTD |  | Program change due to damaged cable 15:10 CTD in / 15:20 CTD out | [7 empty] | CTD | Pos 52°21.132N 2°16.446E | Program change due to damaged cable 15:10 CTD in / 15:20 CTD out |  |  | All | Finished | Area 3a | Possible impact | No impact | 24
2023-10-05 | 16:00 |  |  | 11BU_operations | Belgica | Line | Start | Topas | ACW_04 @6kts SOG | [8 empty] | Topas | ACW_04 @6kts SOG |  | 12 | 2 | All | Finished | Area 3a | No impact | No impact | 25
2023-10-05 | TBC |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | AC 10 | S-going current. Cancelled due to cable rupture (repair needs 24hr to dry) | [7 empty] | Vibrocoring | AC 10 | S-going current. Cancelled due to cable rupture (repair needs 24hr to dry) |  |  | All | Cancelled | Area 3a | Possible impact | No impact | 26
2023-10-05 | TBC |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | AC4 & 1 (TBC) | AC_02: 0,1NM from cable AC_02: < 0,4NM from cable | [7 empty] | Vibrocoring | AC4 & 1 (TBC) | AC_02: 0,1NM from cable AC_02: < 0,4NM from cable |  |  |  | Cancelled |  | Possible impact |  | 27
2023-10-05 | 18:00 |  |  | 11BU_operations | Command | Meeting | Start | Coordination meeting |  | @bridge | [7 empty] | Coordination meeting | @bridge |  |  |  | Command team | Finished | Area 3a | No impact | No impact | 28
2023-10-05 | 18:20 |  |  | 11BU_operations | Belgica | Transit | Start | To Area 3b |  | @ 6kts. Topas on | [7 empty] | Transit | To Area 3b @ 6kts. | Topas on | 16 | 2 |  | Finished |  | No impact | No impact | 29
2023-10-05 | 21:30 |  |  | 11BU_operations | Belgica | Station | Start | [10 empty] | CTD | [5 empty] | Finished | Area 3b | No impact | No impact | 30
2023-10-05 | 22:00 |  |  | 11BU_operations | Belgica | Line | Start | Topas | ACE_07 @5kts SOG | [8 empty] | Topas | ACE_07 @5kts SOG |  | 13.5 | 2.5 | All | Finished | Area 3b | Possible impact | No impact | 31
2023-10-06 | 0:30 |  |  | 11BU_operations | Belgica | Line | Start | Topas | ACE_06 @5kts SOG | [8 empty] | Topas | ACE_06 @5kts SOG |  | 15.5 | 3 | All | Finished | Area 3b | Possible impact | No impact | 32
2023-10-06 | 3:30 |  |  | 11BU_operations | Belgica | Line | Start | Topas | ACE_05 @5kts SOG | [8 empty] | Topas | ACE_05 @5kts SOG |  | 16.5 | 4 | All | Finished | Area 3b | Possible impact | No impact | 33
2023-10-06 | 7:30 |  |  | 11BU_operations | Belgica | Line | Start | Topas | ACE_04 @5kts SOG | Start ivo WMF | [7 empty] | Topas | ACE_04 @5kts SOG | Start ivo WMF | 16 | 3 | All | Finished | Area 3b | Possible impact | Possible impact | 34
2023-10-06 | 8:00 |  |  | 11BU_operations | Crew | Meeting | Start | Crew's meeting |  | @bridge | [7 empty] | Crew's meeting | @bridge |  |  |  | Crew | Finished | Area 3b | No impact | No impact | 35
2023-10-06 | 10:00 |  |  | 11BU_operations | Belgica | Line | Start | Topas | ACE_03 @5kts SOG | [8 empty] | Topas | ACE_03 @5kts SOG |  | 12.5 | 2.5 | All | Finished | Area 3b | Possible impact | Possible impact | 36
2023-10-06 | 12:30 |  |  | 11BU_operations | Belgica | Line | Start | Topas | ACE_02 @5kts SOG | [8 empty] | Topas | ACE_02 @5kts SOG |  | 13 | 3 | All | Finished | Area 3b | Possible impact | Possible impact | 37
2023-10-06 | 15:30 |  |  | 11BU_operations | Belgica | Line | Start | Topas | ACE_01 (E-W) @5kts SOG | [8 empty] | Topas | ACE_01 (E-W) @5kts SOG |  | 8 | 2 | All | Finished | Area 3b | Possible impact | Possible impact | 38
2023-10-06 | 15:45 |  |  | 11BU_operations | Belgica | Station | Start | CTD | End of ACE_01 | [8 empty] | CTD | End of ACE_01 |  |  |  | All | Finished | Area 2 | Possible impact | Possible impact | 39
2023-10-06 | 16:00 |  |  | 11BU_operations | Belgica | Line | Start | Topas | NL_05 (W-E) @5kts SOG | North Hinder North TSS & Maas West Outer TSS | [7 empty] | Topas | NL_05 (W-E) @5kts SOG | North Hinder North TSS & Maas West Outer TSS | 20 | 4 | All | Finished | Area 2 | Possible impact | Possible impact | 40
2023-10-06 | 18:00 |  |  | 11BU_operations | Command team | Meeting | Start | Coordination meeting |  | @bridge | [7 empty] | Coordination meeting | @bridge |  |  |  | Command team | Finished | Area 2 | Possible impact | No impact | 41
2023-10-06 | 20:15 |  |  | 11BU_operations | Belgica | Line | Start | Topas | NL_10 @5kts SOG | North Hinder North TSS & Maas West Outer TSS | [7 empty] | Topas | NL_10 @5kts SOG | North Hinder North TSS & Maas West Outer TSS | 20 | 4 | All | Finished | Area 2 | Possible impact | Possible impact | 42
2023-10-06 | 21:00 |  |  | 11BU_operations | All | Recreation | Start | Rugby |  | @dayroom. FR vs IT. Heading not between 260-280 | [7 empty] | Rugby | @dayroom. FR vs IT | Heading not between 260-280 |  |  | All | Finished |  | Possible impact | No impact | 43
2023-10-07 | 0:00 |  |  | 11BU_operations | Belgica | Line | Start |  |  | North Hinder North TSS & Maas West Outer TSS | [7 empty] | Topas | NL_11 @5kts SOG | North Hinder North TSS & Maas West Outer TSS | 20 | 4 | All | Finished | Area 2 | Possible impact | Possible impact | 44
2023-10-07 | 4:00 |  |  | 11BU_operations | Belgica | Line | Start |  |  | North Hinder North TSS | [7 empty] | Topas | NL_12 @5kts SOG | North Hinder North TSS | 17 | 3.5 | All | Finished | Area 2 | Possible impact | Possible impact | 45
2023-10-07 | 7:20 |  |  | 11BU_operations | Belgica | Line | Start |  |  | North Hinder North TSS | [7 empty] | Topas | NL_13 @5kts SOG | North Hinder North TSS | 20 | 4 | All | Finished | Area 2 | Possible impact | Possible impact | 46
2023-10-07 | 8:00 |  |  | 11BU_operations | Crew | Meeting | Start | [10 empty] | Crew's meeting |  |  |  |  | Crew | Finished | Area 2 | Possible impact | No impact | 47
2023-10-07 | 10:17 |  |  | 11BU_operations | Belgica | Station | Start |  |  | 10:30 CTD on board | [7 empty] | CTD | pos 52°9.437N 3°17.064E | 10:30 CTD on board |  |  | All | Finished | Area 2 | Possible impact | Possible impact | 48
2023-10-07 | 13:00 |  |  | 11BU_operations | Belgica | Line | Start |  |  | TSS crossing | [7 empty] | Topas | NL_14 @5kts SOG | TSS crossing | 26 | 5.5 | All | Finished | Area 2 | Possible impact | Possible impact | 49
2023-10-07 | 14:00 |  |  | 11BU_operations | Crew | Exercise | Start | Fire drill | [9 empty] | Fire drill |  |  |  |  | Crew | Finished |  | No impact | No impact | 50
2023-10-07 | 15:45 |  |  | 11BU_operations | Belgica | Transit | Start | To area 5 |  | at max speed for Topas Follow OSP1 (ETA 00:30), TSS, OSP 4 (ETA 06:00), OSP 5 (ETA 0800) | [7 empty] | Transit | To area 5, at max speed for Topas Follow OSP1 (ETA 00:30), TSS, OSP 4 (ETA 06:00), OSP 5 (ETA 0800) |  | 81 | 9 |  | Finished | Area 4 | No impact | No impact | 51
2023-10-07 | 18:00 |  |  | 11BU_operations | Command team | Meeting | Start | Coordination meeting | [9 empty] | Coordination meeting |  |  |  |  | Command team | Finished | Area 1 | No impact | No impact | 52
2023-10-07 | 20:30 |  |  | 11BU_operations | All | Meeting | Start | briefing project | [9 empty] | briefing project |  | All welcome - science meeting room level 6 |  |  | All | Finished | Area 4 | No impact | No impact | 53
2023-10-07 | 21:00 |  |  | 11BU_operations | Belgica | Station | Start | CTD |  | Along navtrack | [7 empty] | CTD | Along navtrack | 52°44,2N 002°46,2E |  |  |  | Finished | Area 4 | No impact | No impact | 54
2023-10-08 | 0:30 |  |  | 11BU_operations | Belgica | Line | Start | Topas | OSP1 | Along transit, at max speed for Topas on 1 big gen | [7 empty] | Topas | OSP1 | Along transit, at max speed for Topas on 1 big gen |  |  |  | Finished | Area 4 | No impact | No impact | 55
2023-10-08 | o/c |  |  | 11BU_operations | Belgica | Transit | Start |  |  | at max speed for Topas on 1 big gen | [7 empty] | Transit |  | at max speed for Topas on 1 big gen |  |  |  | Finished | Area 4 | No impact | No impact | 56
2023-10-08 | 6:40 |  |  | 11BU_operations | Belgica | Line | Start | Topas | OSP4 | at max speed for Topas on 1 big gen | [7 empty] | Topas | OSP4 | at max speed for Topas on 1 big gen |  |  |  | Finished | Area 4 | No impact | No impact | 57
2023-10-08 | 8:00 |  |  | 11BU_operations | Crew | Meeting | Start | Crew's meeting | [9 empty] | Crew's meeting |  |  |  |  | Crew | Finished | Area 4 | No impact | No impact | 58
2023-10-08 | 8:30 |  |  | 11BU_operations | Belgica | Line | Start | Topas | OSP5 | at 5 kts | [7 empty] | Topas | OSP5 | at 5 kts | 20 | 4 |  | Finished | Area 4 | No impact | No impact | 59
2023-10-08 | 12:30 |  |  | 11BU_operations | Belgica | Line | Start | Topas | DB13 | @5kts | [7 empty] | Topas | DB13 | @5kts | 23 | 5 |  | Finished | Area 5 | No impact | No impact | 60
2023-10-08 | 14:00 |  |  | 11BU_operations |  | Meeting | Start | Safety committee | [9 empty] | Safety committee | [5 empty] | Finished | Area 5 | No impact | No impact | 61
2023-10-08 | 17:30 |  |  | 11BU_operations | Belgica | Line | Start | Topas | DB14 | @5kts | [7 empty] | Topas | DB14 | @5kts | 25 | 5 |  | Finished | Area 5 | No impact | No impact | 62
2023-10-08 | 18:00 |  |  | 11BU_operations | Command team | Meeting | Start | Coordination meeting | [9 empty] | Coordination meeting |  |  |  |  | Command team | Finished | Area 5 | No impact | No impact | 63
2023-10-08 | 21:00 |  |  | 11BU_operations | Belgica | Station | Start | CTD |  | 54°38,0N 003°17,6E | [7 empty] | CTD |  | 54°38,0N 003°17,6E |  |  |  | Finished | Area 5 | No impact | No impact | 64
2023-10-08 | 22:30 |  |  | 11BU_operations | Belgica | Line | Start | Topas | DB15 | @5kts | [7 empty] | Topas | DB15 | @5kts | 11 | 2 |  | Finished | Area 5 | No impact | No impact | 65
2023-10-08 | 0:30 |  |  | 11BU_operations | Belgica | Line | Start | Topas | DB16 | @5kts | [7 empty] | Topas | DB16 | @5kts | 22 | 5 |  | Finished | Area 5 | No impact | No impact | 66
2023-10-09 | 6:10 |  |  | 11BU_operations | Belgica | Line | Start | Topas | DB17, pt 1 | @5kts | [7 empty] | Topas | DB17, pt 1 | @5kts | 19 | 4 |  | Finished | Area 5 | No impact | No impact | 67
2023-10-09 | 8:00 |  |  | 11BU_operations | Crew | Meeting | Start | Crew's meeting | [9 empty] | Crew's meeting |  |  |  |  | Crew | Finished | Area 5 | No impact | No impact | 68
2023-10-09 | 9:00 |  |  | 11BU_operations | Belgica | Station | Start | CTD |  | position: 54°41.3187N 2°56.9209E | [7 empty] | CTD |  | position: 54°41.3187N 2°56.9209E |  |  |  | Finished | Area 5 | No impact | No impact | 69
2023-10-09 | 10:00 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | VC03 | 1010 VC In, heading 300, pos 54°39.325N 003°0.373E / 1017 VC Out | [7 empty] | Vibrocoring | VC03 | 1010 VC In, heading 300, pos 54°39.325N 003°0.373E / 1017 VC Out |  |  |  | Finished | Area 5 | No impact | No impact | 70
2023-10-09 | 10:45 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | VC04 | heading 305, pos 54°39.533N 3°0.616E / 1052 VC in / 1059 VC out | [7 empty] | Vibrocoring | VC04 | heading 305, pos 54°39.533N 3°0.616E / 1052 VC in / 1059 VC out |  |  |  | Finished | Area 5 | No impact | No impact | 71
2023-10-09 | 10:22 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | 0 | heading 305, pos 54°39.166N 3°0.191E / 1124 VC in / 1131 VC out | [7 empty] | Vibrocoring | 0 | heading 305, pos 54°39.166N 3°0.191E / 1124 VC in / 1131 VC out |  |  |  | Finished | Area 5 | No impact | No impact | 72
2023-10-09 | 11:50 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | VC01 | heading 305, pos 54°38.746N 2°59.711E / 1158 VC in / 1206 VC out | [7 empty] | Vibrocoring | VC01 | heading 305, pos 54°38.746N 2°59.711E / 1158 VC in / 1206 VC out |  |  |  | Finished | Area 5 | No impact | No impact | 73
2023-10-09 | 12:30 |  |  | 11BU_operations | Belgica | Line | Start | Topas | DB 17, pt 2 | @5kts | [7 empty] | Topas | DB 17, pt 2 | @5kts | 27 | 6 |  | Finished | Area 5 | No impact | No impact | 74
2023-10-09 | 13:30 |  |  | 11BU_operations | Belgica | Line | Start | Topas | DB18, pt 1 | @5kts | [7 empty] | Topas | DB18, pt 1 | @5kts |  |  |  | Finished | Area 5 | No impact | No impact | 75
2023-10-09 | 15:00 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | VC05 | heading 325 , pos 54°40.467N 2°1.685E / 1502 VC in / 1508 VC out | [7 empty] | Vibrocoring | VC05 | heading 325 , pos 54°40.467N 2°1.685E / 1502 VC in / 1508 VC out |  |  |  | Finished | Area 5 | No impact | No impact | 76
2023-10-09 | 15:30 |  |  | 11BU_operations |  | Transit | Start | To Vibrocore position | [9 empty] | Transit | To Vibrocore position |  |  |  |  | Finished | Area 5 | No impact | No impact | 77
2023-10-09 | 17:00 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | VC10 | Pos: 54°47.968N-003°20.715E heading 302 / 1649 VC in / 1658 VC out | [7 empty] | Vibrocoring | VC10 | Pos: 54°47.968N-003°20.715E heading 302 / 1649 VC in / 1658 VC out |  |  |  | Finished | Area 5 | No impact | No impact | 78
2023-10-09 | 17:15 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | VC09 | Pos: 54°48.083N-003°20.358E heading 302 / 1716 VC in / 1725 VC out | [7 empty] | Vibrocoring | VC09 | Pos: 54°48.083N-003°20.358E heading 302 / 1716 VC in / 1725 VC out |  |  |  | Finished | Area 5 | No impact | No impact | 79
2023-10-09 | 18:00 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | VC08 | Pos: 54°48.292N-003°19.737E heading 300 / 1746 VC in / 1754 VC out | [7 empty] | Vibrocoring | VC08 | Pos: 54°48.292N-003°19.737E heading 300 / 1746 VC in / 1754 VC out |  |  |  | Finished | Area 5 | No impact | No impact | 80
2023-10-09 | 18:30 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | VC06 | Pos: 54°48.637N-003°18.702E heading 305 / 1820 VC in / 1829 VC out / 3m ahead pos: 54°48.638N-003°18.700E / 1843 VC in / 1853 VC out | [7 empty] | Vibrocoring | VC06 | Pos: 54°48.637N-003°18.702E heading 305 / 1820 VC in / 1829 VC out / 3m ahead pos: 54°48.638N-003°18.700E / 1843 VC in / 1853 VC out |  |  |  | Finished | Area 5 | No impact | No impact | 81
2023-10-09 | 19:30 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | VC07 | Pos: 54°49.670N-003°20.114E heading 305 / 1922 VC in / 1931 VC OUT | [7 empty] | Vibrocoring | VC07 | Pos: 54°49.670N-003°20.114E heading 305 / 1922 VC in / 1931 VC OUT |  |  |  | Finished | Area 5 | No impact | No impact | 82
2023-10-09 |  |  |  | 11BU_operations | Belgica | Station | Start | CTD |  | CTD in same position as last core | [7 empty] | CTD |  | CTD in same position as last core |  |  |  | Finished |  |  |  | 83
2023-10-09 | 19:30 |  |  | 11BU_operations |  | Transit | Start | to DB 18, pt 2 |  | 6,5kts | [7 empty] | Transit | to DB 18, pt 2 | 6,5kts |  |  |  | Finished | Area 5 | No impact | No impact | 84
2023-10-09 | TBD |  |  | 11BU_operations | Command team | Meeting | Start | Coordination meeting | [9 empty] | Coordination meeting |  |  |  |  | Command team | Finished | Area 5 | No impact | No impact | 85
2023-10-09 | 22:00 |  |  | 11BU_operations | Belgica | Line | Start | Topas | DB18, pt 2 | 6,5kts | [7 empty] | Topas | DB18, pt 2 | 6,5kts | 20 | 3.5 |  | Finished | Area 5 | No impact | No impact | 86
2023-10-10 | 1:30 |  |  | 11BU_operations | Belgica | Line | Start | Topas | DB19 | 6,5kts | [7 empty] | Topas | DB19 | 6,5kts | 11 | 2 |  | Finished | Area 5 | No impact | No impact | 87
2023-10-10 | 3:30 |  |  | 11BU_operations | Belgica | Line | Start | Topas | DB20 | 6,5kts | [7 empty] | Topas | DB20 | 6,5kts | 17 | 3 |  | Finished | Area 5 | No impact | No impact | 88
2023-10-10 | 5:45 |  |  | 11BU_operations |  | Transit | Start | To Vibrocore position |  | max speed | [7 empty] | transit | To Vibrocore position | max speed | 23 | 3 |  | Finished | Area 6 | No impact | No impact | 89
2023-10-10 | 8:00 |  |  | 11BU_operations |  | Meeting | Start | Crew's meeting | [9 empty] | Crew's meeting |  |  |  |  | Crew | Finished | Area 6 | No impact | No impact | 90
2023-10-10 | 8:44 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring (TBC) | OG05 | In position 54°22.347N 4°7.880E, heading 221 / 0846 VC In / 0856 VC out | [7 empty] | Vibrocoring (TBC) | OG05 | In position 54°22.347N 4°7.880E, heading 221 / 0846 VC In / 0856 VC out |  |  |  | Finished | Area 6 | No impact | No impact | 91
2023-10-10 | 9:26 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | OG04 | In position 54°22.222N 4°5.435E, heading 235 / 0928VC In / 0937 VC out | [7 empty] | Vibrocoring | OG04 | In position 54°22.222N 4°5.435E, heading 235 / 0928VC In / 0937 VC out |  |  |  | Finished | Area 6 | No impact | No impact | 92
2023-10-10 | 9:40 |  |  | 11BU_operations |  | Transit | Start | to OG3 | [9 empty] | transit | to OG3 |  |  |  |  | Finished | Area 6 | No impact | No impact | 93
2023-10-10 | 10:30 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | OG3 | In position 54°21.696N 3°55.127E, heading 255 / 1034 VC In / 1042 VC out | [7 empty] | Vibrocoring | OG3 | In position 54°21.696N 3°55.127E, heading 255 / 1034 VC In / 1042 VC out |  |  |  | Finished | Area 6 | No impact | No impact | 94
2023-10-10 | 10:45 |  |  | 11BU_operations |  | Transit | Start | to OG2 | [9 empty] | transit | to OG2 |  |  |  |  | Finished | Area 6 | No impact | No impact | 95
2023-10-10 | 11:30 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | OG2 | In position 54°21.197N 3°45.308E, heading 220 / 1138 VC In / 1145 VC out / 5m ahead / 1155 VC In / 1207 VC out | [7 empty] | Vibrocoring | OG2 | In position 54°21.197N 3°45.308E, heading 220 / 1138 VC In / 1145 VC out / 5m ahead / 1155 VC In / 1207 VC out |  |  |  | Finished | Area 6 | No impact | No impact | 96
2023-10-10 | 12:10 |  |  | 11BU_operations |  | Transit | Start | to OG1 | [9 empty] | Transit | to OG1 |  |  |  |  | Finished | Area 6 | No impact | No impact | 97
2023-10-10 | 12:30 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | OG1 | In position 54°20.929N 3°40.049E, heading 214 / 1248 VC In / 1256 VC out | [7 empty] | Vibrocoring | OG1 | In position 54°20.929N 3°40.049E, heading 214 / 1248 VC In / 1256 VC out |  |  |  | Finished | Area 6 | No impact | No impact | 98
2023-10-10 | 13:00 |  |  | 11BU_operations | Belgica | Station | Start | CTD | [9 empty] | CTD | [5 empty] | Finished | Area 6 | No impact | No impact | 99
2023-10-10 | 14:00 |  |  | 11BU_operations |  | Transit | Start | to OG01 W side |  | max speed on 1 DG | [7 empty] | transit | to OG01 W side | max speed on 1 DG | 10 | 1 |  | Finished | Area 6 | No impact | No impact | 100
2023-10-10 | 15:00 |  |  | 11BU_operations | Belgica | Line | Start | Topas | OG01 | 9kts | [7 empty] | Topas | OG01 | 9kts | 33 | 4 |  | Finished | Area 6 | No impact | No impact | 101
2023-10-10 | 18:00 |  |  | 11BU_operations | Command team | Meeting | Start | Coordination meeting | [9 empty] | Coordination meeting |  |  |  |  | Command team | Finished | Area 6 | No impact | No impact | 102
2023-10-10 | 18:30 |  |  | 11BU_operations |  | Transit | Start |  |  | max speed on 1 DG | [7 empty] | Transit |  | max speed on 1 DG | 10 | 1 |  | Finished |  |  |  | 103
2023-10-10 | 19:30 |  |  | 11BU_operations | Belgica | Line | Start | Topas | OG03 | 6,5 kts | [7 empty] | Topas | OG03 | 6,5 kts | 8.5 | 1.5 |  | Finished | Area 6 | No impact | No impact | 104
2023-10-10 | 20:00 |  |  | 11BU_operations | Everyone is welcone | Meeting | Start | Silke's talk |  | Silke will give a talk about her research; level 6; science meeting room; all welcome | [7 empty] | Silke's talk | Silke will give a talk about her research; level 6; science meeting room; all welcome |  |  |  | Everyone is welcone | Finished | Area 6 | No impact | No impact | 105
2023-10-10 | 21:00 |  |  | 11BU_operations |  | Transit | Start |  |  | max speed on 1 DG | [7 empty] | Transit |  | max speed on 1 DG | 1.3 | 0.5 |  | Finished |  |  |  | 106
2023-10-10 | 21:30 |  |  | 11BU_operations | Belgica | Line | Start | Topas | OG04 | 6,5 kts | [7 empty] | Topas | OG04 | 6,5 kts | 8.5 | 1.5 |  | Finished | Area 6 | No impact | No impact | 107
2023-10-10 | 23:00 |  |  | 11BU_operations |  | Transit | Start |  |  | max speed on 1 DG | [7 empty] | Transit |  | max speed on 1 DG | 6 | 1 |  | Finished |  |  |  | 108
2023-10-11 | 0:00 |  |  | 11BU_operations | Belgica | Line | Start | Topas | OG05 | 6,5 kts | [7 empty] | Topas | OG05 | 6,5 kts | 8.5 | 1.5 |  | Finished | Area 6 | No impact | No impact | 109
2023-10-11 | 1:30 |  |  | 11BU_operations |  | Transit | Start |  |  | max speed on 1 DG | [7 empty] | Transit |  | max speed on 1 DG | 6 | 0.5 |  | Finished |  |  |  | 110
2023-10-11 | 2:00 |  |  | 11BU_operations | Belgica | Line | Start | Topas | OG06 | 6,5 kts - if need be, skip this one Partially finished, in order to be in time in CTD station | [7 empty] | Topas | OG06 | 6,5 kts - if need be, skip this one Partially finished, in order to be in time in CTD station | 8.5 | 1.5 |  | Finished | Area 6 | No impact | No impact | 111
2023-10-11 | 3:30 |  |  | 11BU_operations |  | Transit | Start | from OG06 to CTD |  | max speed on 1 DG | [7 empty] | transit from OG06 to CTD |  | max speed on 1 DG | 37 | 4 |  | Finished |  |  |  | 112
2023-10-11 | 6:00 |  |  | 11BU_operations | Belgica | Station | Start | CTD | OSP01 | [8 empty] | CTD | OSP01 | 54°07.0512N 2°41.0453E |  |  |  | Finished | Area 4 | No impact |  | 113
2023-10-11 | 6:30 |  |  | 11BU_operations |  | Transit | Start | to CTD | [9 empty] | transit to CTD |  |  | 14 | 1.5 |  | Finished | Area 4 | No impact |  | 114
2023-10-11 | 8:00 |  |  | 11BU_operations | Crew | Meeting | Start | Crew's meeting | [9 empty] | Crew's meeting |  |  |  |  | Crew | Finished | Area 4 | No impact | No impact | 115
2023-10-11 | 8:25 |  |  | 11BU_operations | Belgica | Station | Start | CTD | OSP04 | [8 empty] | CTD | OSP04 | 53°57.4307N 2°56.9838E |  |  |  | Finished | Area 4 | No impact |  | 116
2023-10-11 | 8:50 |  |  | 11BU_operations |  | Transit | Start |  |  | 4 | [7 empty] | Transit |  | 4 | 105 | 13 |  | Finished | Area 4 | No impact |  | 117
2023-10-11 | 18:00 |  |  | 11BU_operations | Command team | Meeting | Start | Coordination meeting | [9 empty] | Coordination meeting |  |  |  |  | Command team | Finished | Area 1 | No impact | No impact | 118
2023-10-11 | 21:30 |  |  | 11BU_operations |  | Deployment | Start | Sparker |  | current: 1,2kts, dir: 203 2,5NM before start of SB_08, reduce speed to min manoeuvring speed and preapre aft deck. Deplo gear when ready | [7 empty] | Sparker deployement | current: 1,2kts, dir: 203 2,5NM before start of SB_08, reduce speed to min manoeuvring speed and preapre aft deck. Deplo gear when ready |  |  |  |  | Finished | Area 1 | No impact |  | 119
2023-10-11 | 22:30 |  |  | 11BU_operations | All | Line | Start | Sparker & Topas | SB_08 (W-E) @3,5kts SOG | [8 empty] | Sparker & Topas | SB_08 (W-E) @3,5kts SOG |  | 24 | 6.8571 | All | Finished | Area 1 | No impact | No impact | 120
2023-10-12 | 6:30 |  |  | 11BU_operations | All | Line | Start | Sparker & Topas | SB_07 @3,5kts STW | [8 empty] | Sparker & Topas | SB_07 @3,5kts STW |  | 22 | 6.2857 | All | Finished | Area 1 | No impact | No impact | 121
2023-10-12 | 8:00 |  |  | 11BU_operations | Crew | Meeting | Start | Crew's meeting | [9 empty] | Crew's meeting |  |  |  |  | Crew | Finished | Area 1 | No impact | No impact | 122
2023-10-12 | 10:00 |  |  | 11BU_operations | All | Line | Start | Sparker & Topas | SB_06 @3,5kts STW | [8 empty] | Sparker & Topas | SB_06 @3,5kts STW |  | 19 | 5.4286 | All | Finished | Area 1 | No impact | No impact | 123
2023-10-12 | 14:30 |  |  | 11BU_operations | Crew | Meeting | Start | Bomb threat briefing |  | Conference room | [7 empty] | Bomb threat briefing |  | Conference room |  |  | Crew | Finished | Area 1 | No impact | No impact | 124
2023-10-12 | 16:00 |  |  | 11BU_operations | Crew | Testing | Start | SSAS test | [9 empty] | SSAS test |  |  |  |  | Crew | Finished | Area 1 | No impact | No impact | 125
2023-10-12 | 16:00 |  |  | 11BU_operations | All | Line | Start | Sparker & Topas | SB_05 @3,5kts STW | [8 empty] | Sparker & Topas | SB_05 @3,5kts STW |  | 23 | 6.5714 | All | Finished | Area 1 | No impact | No impact | 126
2023-10-12 | 18:00 |  |  | 11BU_operations | Command team | Meeting | Start | Coordination meeting | [9 empty] | Coordination meeting |  |  |  |  | Command team | Finished | Area 1 | No impact | No impact | 127
2023-10-13 | 23:00 |  |  | 11BU_operations | All | Line | Start | Sparker & Topas | SB_04 @3,5kts STW | [8 empty] | Sparker & Topas | SB_04 @3,5kts STW |  | 27 | 7.7143 | All | Finished | Area 1 | Possible impact | No impact | 128
2023-10-13 | 4:30 |  |  | 11BU_operations |  | Recovery | Start | Sparker |  | When weather has deteriorated and image is to bad. Wake up CO and Sparker technician first in order to evaluate. After decision, wake up boatswain & 2nd boatswain 15' in advance. Expected around 0500 | [7 empty] | Sparker recovery | When weather has deteriorated and image is to bad. Wake up CO and Sparker technician first in order to evaluate. After decision, wake up boatswain & 2nd boatswain 15' in advance. | Expected around 0500 |  |  |  | Finished | Area 1 | Possible impact |  | 129
2023-10-13 | 5:30 |  |  | 11BU_operations | Belgica | Line | Start | Topas | SB_03 @6kts SOG | Until image deteriorates | [7 empty] | Topas | SB_03 @6kts SOG | Until image deteriorates | 24 | 6.8571 | All | Finished | Area 1 | Possible impact | No impact | 130
2023-10-13 | 8:00 |  |  | 11BU_operations | Crew | Meeting | Start | Crew's meeting | [9 empty] | Crew's meeting |  |  |  |  | Crew | Finished | Area 1 | No impact | No impact | 131
2023-10-13 | 9:00 |  |  | 11BU_operations | Belgica | Line | Start | Topas | SB_02 @6kts SOG | North Hinder South & Sunk TSS | [7 empty] | Topas | SB_02 @6kts SOG | North Hinder South & Sunk TSS | 23 | 6.5714 | All | Finished | Area 1 | Possible impact | Possible impact | 132
2023-10-13 | 13:15 |  |  | 11BU_operations | All | Transit | Start | ???? This is both a transit and arriving at a station | [9 empty] | Transit/Topas | SB_01 (E-W) @6kts SOG | Bad quality due to weather. Intend to sail at higher speed to other side and start with currents in the back . | 27 | 7.7143 | All | Finished | Area 1 | Possible impact | Possible impact | 133
2023-10-13 | TBD |  |  | 11BU_operations |  | Sheltering | Start | N of WMF / UK anchor area | [9 empty] | Sheltering | N of WMF / UK anchor area |  |  |  |  | Cancelled | Area 1 | Possible impact |  | 134
2023-10-13 | 16:05 |  |  | 11BU_operations | Belgica | Line | Start | Topas | SB_01 (E-W) @6kts SOG | [8 empty] | Topas | SB_01 (E-W) @6kts SOG |  | 27 |  |  | Finished | Area 1 | Possible impact | Possible impact | 135
2023-10-13 | 16:10 |  |  | 11BU_operations |  | ???? | Start | ???? | [9 empty] | Slow flooding incident | In hospital. Rupture of hot water pipe, causing smoke detection system to go off. No impact on mission. Impact on hospital TBC. |  |  |  |  | Finished | Area 1 | No impact | No impact | 136
2023-10-13 | 18:00 |  |  | 11BU_operations | Command team | Meeting | Start | Coordination meeting | [9 empty] | Coordination meeting |  |  |  |  | Command team | Finished | Area 1 | No impact | No impact | 137
2023-10-13 | 20:30 |  |  | 11BU_operations | Belgica | Station | Start | CTD | Start of line SB_11 | [8 empty] | CTD | Start of line SB_11 |  |  |  |  | Finished | Area 1 |  |  | 138
2023-10-13 | 21:00 |  |  | 11BU_operations | Belgica | Line | Start | Topas | SB_11 @6kts SOG | 2 | [7 empty] | Topas | SB_11 @6kts SOG | 2 | 27 | 7.7143 | All | Finished | Area 1 | Possible impact | Possible impact | 139
2023-10-14 | 1:30 |  |  | 11BU_operations | Belgica | Station | Start | CTD | [9 empty] | CTD | [5 empty] | Finished | Area 1 | Possible impact | No impact | 140
2023-10-14 | 2:00 |  |  | 11BU_operations | Belgica | Line | Start | Topas | SB_10 @6kts SOG | With direction TSS | [7 empty] | Topas | SB_10 @6kts SOG | With direction TSS | 27 | 7.7143 | All | Finished | Area 1 | Possible impact | Possible impact | 141
2023-10-14 | 6:00 |  |  | 11BU_operations |  | Transit | Start | ???? This is both a transit and arriving at a station | [9 empty] | Transit/Topas | To test zone |  |  |  |  | Finished | Area 1 |  |  | 142
2023-10-14 | 8:00 |  |  | 11BU_operations |  | Meeting | Start | Crew's meeting | [9 empty] | Crew's meeting | [5 empty] | Finished | Area 1 | No impact | No impact | 143
2023-10-14 | 8:00 |  |  | 11BU_operations |  | Testing | Start | DP tests | [9 empty] | DP tests | [5 empty] | Finished | Area 1 | Possible impact | No impact | 144
2023-10-14 | 10:00 |  |  | 11BU_operations |  | Testing | Start | ADCP test | [9 empty] | ADCP test | [5 empty] | Finished | Area 1 | Possible impact | No impact | 145
2023-10-14 | 13:00 |  |  | 11BU_operations |  | Transit | Start | [10 empty] | Transit | [5 empty] | Ongoing | Area 1 | No impact | No impact | 146
2023-10-14 | 14:00 |  |  | 11BU_operations | Crew | Meeting | Start | briefing project | [9 empty] | briefing project | For crew |  |  |  |  | Ongoing | Area 1 | No impact | No impact | 147
2023-10-07 | 14:00 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | DCS_VC01 | Direction( S-N)dependant on current ==> point order might change | [7 empty] | Vibrocoring | DCS_VC01 | Direction( S-N)dependant on current ==> point order might change |  |  | All | Cancelled | Area 2 | Possible impact | No impact | 148
2023-10-07 | 15:00 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | DCS_VC02 | Direction( S-N)dependant on current ==> point order might change | [7 empty] | Vibrocoring | DCS_VC02 | Direction( S-N)dependant on current ==> point order might change |  |  | All | Cancelled | Area 2 | Possible impact | No impact | 149
2023-10-07 | 16:00 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | DCS_VC03 | Direction( S-N)dependant on current ==> point order might change | [7 empty] | Vibrocoring | DCS_VC03 | Direction( S-N)dependant on current ==> point order might change |  |  | All | Cancelled | Area 2 | Possible impact | No impact | 150
2023-10-07 | 17:00 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | DCS_VC04 | Direction( S-N)dependant on current ==> point order might change | [7 empty] | Vibrocoring | DCS_VC04 | Direction( S-N)dependant on current ==> point order might change |  |  | All | Cancelled | Area 2 | Possible impact | No impact | 151
2023-10-07 | 18:00 |  |  | 11BU_operations | Belgica | Station | Start | CTD | CTD_NL_02 | [8 empty] | CTD | CTD_NL_02 |  |  |  | All | Cancelled | Area 2 | No impact | No impact | 152
2023-10-10 | 9:00 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring |  | Time/Place issue. Should start transit at 06:00 iot arrive at 09:00. Prio? From this moment, end of torough analysis of operational course. 8 cores are mentioned in plan, however only 6 positions available. In deep water route. AX_VC17: 0,47NM from cable AX_VC20: 0,1NM from pipe | [7 empty] | Vibrocoring |  | Time/Place issue. Should start transit at 06:00 iot arrive at 09:00. Prio? From this moment, end of torough analysis of operational course. 8 cores are mentioned in plan, however only 6 positions available. In deep water route. AX_VC17: 0,47NM from cable AX_VC20: 0,1NM from pipe |  |  | All | Cancelled | Area 3b |  | Possible impact | 153
2023-10-14 | 17:30 |  |  | 11BU_operations | All | Cruise |  | Breakwaters Zeebrugge | [9 empty] | ETA | Breakwaters Zeebrugge |  |  |  | All | Planned | BEL Inshore | No impact | No impact | 154
2023-10-14 | 18:32 |  |  | 11BU_operations | All | Cruise | End | Naval port Zeebrugge | [9 empty] | ETA | Naval port Zeebrugge |  |  |  | All | Planned | BEL Inshore | No impact | No impact | 155
2023-10-14 | O/C mooring |  |  | 11BU_operations |  | ???? | Start | [10 empty] | Payment meal + goodies | In conference room | Put in order for goodies NLT 1800 in conference room | [7 empty] | 156
2023-10-14 | 20:00 |  |  | 11BU_operations | Scientists | Meeting | Start | science debrief |  | Scientists gather in conference room for final debrief | [7 empty] | science debrief | Scientists gather in conference room for final debrief |  |  |  | Scientists |  |  |  |  | 157
2023-10-15 | 8:00 |  |  | 11BU_operations |  | Meeting | Start | Crew's meeting |  | In scientist lab | [7 empty] | Crew's meeting |  | In scientist lab | [7 empty] | 158
2023-10-15 | o/c |  |  | 11BU_operations |  | Meeting | Start | Coordination meeting |  | CO, chief engineer, chief mate, electronician, boatswain, Lt Nav. In scientist lab Overview of 16 - 20 okt | [7 empty] | Coordination meeting | CO, chief engineer, chief mate, electronician, boatswain, Lt Nav | In scientist lab Overview of 16 - 20 okt | [7 empty] | 159
2023-10-15 | 8:00 |  |  | 11BU_operations | All | Demobilisation | Start |  |  | Vibrocorrer will stay ashore until Tuesday | [7 empty] | Demob |  | Vibrocorrer will stay ashore until Tuesday |  |  | All | Planned | BEL Inshore | No impact | No impact | 160
|  |  |  | 11BU_operations |  | Demobilisation
11BU_operations
11BU_operations
|  |  |  | 11BU_operations |  | Cruise
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
11BU_operations
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00
|  |  |  | 11BU_operations | 0:00

## events
Date | Hour | Actor | eventDefinitionId | Program | Tool | Process | Action | Label | Station | Description | Remarks | Dist | Time | Status | Region | Weather | Navigation | Subject | Description2 | Remarks2 | Dist (nm)2 | Time (u)3 | For4 | Status5 | Region6 | Weather7 | Navigation8 | original order
2023-10-04 | 9:00 |  |  | 11BU_operations | Crew | ???? | Start | [10 empty] | Provision delivery |  |  |  |  | Crew | Finished | BEL Inshore | No impact | No impact | 3
2023-10-13 | 16:10 |  |  | 11BU_operations |  | ???? | Start | ???? | [9 empty] | Slow flooding incident | In hospital. Rupture of hot water pipe, causing smoke detection system to go off. No impact on mission. Impact on hospital TBC. |  |  |  |  | Finished | Area 1 | No impact | No impact | 136
2023-10-14 | O/C mooring |  |  | 11BU_operations |  | ???? | Start | [10 empty] | Payment meal + goodies | In conference room | Put in order for goodies NLT 1800 in conference room | [7 empty] | 156
2023-10-14 | 17:30 |  |  | 11BU_operations | All persons | Cruise | End | Breakwaters Zeebrugge | [9 empty] | ETA | Breakwaters Zeebrugge |  |  |  | All | Planned | BEL Inshore | No impact | No impact | 154
2023-10-14 | 18:32 |  |  | 11BU_operations | All persons | Cruise | End | Naval port Zeebrugge | [9 empty] | ETA | Naval port Zeebrugge |  |  |  | All | Planned | BEL Inshore | No impact | No impact | 155
2023-10-04 | 14:30 |  |  | 11BU_operations | Belgica | Cruise | Start |  |  | When installation of pCO² system is completed. After heli exercise in dock sheduled between 1300 & 1500) | [7 empty] | ETD |  | When installation of pCO² system is completed. After heli exercise in dock sheduled between 1300 & 1500) |  |  | All | Finished | BEL Inshore | No impact | Possible impact | 6
2023-10-15 | 8:00 |  |  | 11BU_operations | All persons | Demobilisation | Start |  |  | Vibrocorrer will stay ashore until Tuesday | [7 empty] | Demob |  | Vibrocorrer will stay ashore until Tuesday |  |  | All | Planned | BEL Inshore | No impact | No impact | 160
2023-10-11 | 21:30 |  |  | 11BU_operations |  | Deployment | Start | Sparker |  | current: 1,2kts, dir: 203 2,5NM before start of SB_08, reduce speed to min manoeuvring speed and preapre aft deck. Deplo gear when ready | [7 empty] | Sparker deployement | current: 1,2kts, dir: 203 2,5NM before start of SB_08, reduce speed to min manoeuvring speed and preapre aft deck. Deplo gear when ready |  |  |  |  | Finished | Area 1 | No impact |  | 119
2023-10-04 | o/c |  |  | 11BU_operations | All persons | Exercise | Start | Abandon ship exercise | [9 empty] | Abandon ship exercise |  |  |  |  | All | Finished | BEL TTW | No impact | No impact | 8
2023-10-04 | o/c |  |  | 11BU_operations | All persons | Exercise | Start | FF exercise | [9 empty] | FF exercise |  |  |  |  | All | Finished | BEL EEZ | No impact | No impact | 9
2023-10-15 | o/c |  |  | 11BU_operations | Command | Meeting | Start | Coordination meeting |  | CO, chief engineer, chief mate, electronician, boatswain, Lt Nav. In scientist lab Overview of 16 - 20 okt | [7 empty] | Coordination meeting | CO, chief engineer, chief mate, electronician, boatswain, Lt Nav | In scientist lab Overview of 16 - 20 okt | [7 empty] | 159
2023-10-04 | 7:00 |  |  | 11BU_operations | Belgica | Mobilisation | Start | [10 empty] | Start mobilization |  |  |  |  | All | Finished | BEL Inshore | No impact | No impact | 1
|  |  |  | 11BU_operations | Topas | Operation | Start
2023-10-13 | 4:30 |  |  | 11BU_operations | Sparker | Recovery | Start | Sparker |  | When weather has deteriorated and image is to bad. Wake up CO and Sparker technician first in order to evaluate. After decision, wake up boatswain & 2nd boatswain 15' in advance. Expected around 0500 | [7 empty] | Sparker recovery | When weather has deteriorated and image is to bad. Wake up CO and Sparker technician first in order to evaluate. After decision, wake up boatswain & 2nd boatswain 15' in advance. | Expected around 0500 |  |  |  | Finished | Area 1 | Possible impact |  | 129
2023-10-06 | 21:00 |  |  | 11BU_operations | All persons | Recreation | Start | Rugby |  | @dayroom. FR vs IT. Heading not between 260-280 | [7 empty] | Rugby | @dayroom. FR vs IT | Heading not between 260-280 |  |  | All | Finished |  | Possible impact | No impact | 43
2023-10-13 | TBD |  |  | 11BU_operations |  | Sheltering | Start | N of WMF / UK anchor area | [9 empty] | Sheltering | N of WMF / UK anchor area |  |  |  |  | Cancelled | Area 1 | Possible impact |  | 134
2023-10-05 | 9:30 |  |  | 11BU_operations | Belgica | Station | Start | Vibrocoring | AC 07 | N-going current 09:38 VC in, heading 217, pos 52°22.011N 2°16.080E / 0952 VC out | [7 empty] | Vibrocoring | AC 07 | N-going current 09:38 VC in, heading 217, pos 52°22.011N 2°16.080E / 0952 VC out |  |  | All | Finished | Area 3a | No impact | No impact | 18
[8 empty] | Vibrocoring | AC 07 | N-going current 09:38 VC in, heading 217, pos 52°22.011N 2°16.080E / 0952 VC out | [7 empty] | Vibrocoring | AC 07 | N-going current 09:38 VC in, heading 217, pos 52°22.011N 2°16.080E / 0952 VC out |  |  | All | Finished | Area 3a | No impact | No impact | 18

## process mapping
Bomb threat briefing | Meeting | Start
Coordination meeting | Meeting | Start
Crew's meeting | Meeting | Start
Daily meeting crew (TBC) | Meeting | Start
Operational meeting | Meeting | Start
Safety briefing | Meeting | Start
Safety committee | Meeting | Start
Silke's talk | Meeting | Start
briefing project | Meeting | Start
science debrief | Meeting | Start
ETA | Cruise | End
ETD | Cruise | Start
Abandon ship exercise | Exercise | Start
FF exercise | Exercise | Start
Fire drill | Exercise | Start
Demob | Demobilisation | Start
Start mobilization | Mobilisation | Start
Rugby | Recreation | Start
ADCP test | Testing | Start
Transit | Transit | Start
Transit/Topas | Transit | Start
transit | Transit | Start |  | Distinct
transit | Transit | Start
transit from OG06 to CTD | Transit | Start |  | Cruise
transit to CTD | Transit | Start |  | Demobilisation
CTD | Station | Start |  | Deployment
DP tests | Testing | Start | dynamic propulsion | Exercise | new
Payment meal + goodies |  |  |  | Meeting | new
Provision delivery |  |  |  | Mobilisation
SSAS test | Testing | Start | ship security alert system | Recovery
Sheltering | Sheltering |  |  | Recreation | new
Slow flooding incident |  |  |  | Station
Sparker & Topas | Line | Start |  | Testing | new
Sparker deployement | Deployment | Start |  | Transit
Sparker recovery | Recovery | Start |  | Sheltering | new
Topas | Line | Start
Vibrocoring | Station | Start |  | Administration